## Introduction
Introduction to the FIS COVID-19 Toolkit
Updated 11th June 2020
Latest update 19th May 2020
Dear Colleague
As the COVID-19 situation evolves, the industry is moving into the restart phase with some companies effectively coming out of hibernation and others trying to scale back up. This tool is based on key concerns that have been identified and raised through the FIS community.
This tool covers a basic bank of questions covering the key areas of:
Safety | People | Commercial and Legal | Supply Chain | Cash Flow
The aim is to extend and refine as new questions come in and advice is developed and we'll issue essential update bulletins when new advice becomes available. To ensure this resource is concise and accurate we are working closely with the civil service, fellow trade associations, our umbrella bodies BuildUK and the Construction Products Association and of course our community of members. Advice on completing the register is presented to the right of this text.
Of all the challenges our members face, balancing cash in a market that is already short of credit is perhaps the most difficult. Early and decisive action is critical to ensuring that your business emerges from any unsettled period. FIS is writing to the supply chain to understand and encourage careful credit management to ensure that, when the market does pick up again, our membership is ready to support the revival of the UK construction sector.
Please do send all questions and comments directly to myself and we'll do what we can to hunt out the answers as quickly as we can. FIS talks alot about community and we will do all we can to ensure our community rallies, to this end please do not hesitate to email or call, whether it be to seek advice, feed in your views or simply to chat through any concerns that you have.
All the very best,
Iain
Iain McIlwee
CEO, Finishes and Interiors Sector Limited
E: iainmcilwee@thefis.org T: 07792 959 481

## Risk Register
COVID Return to Work Risk Management Checklist | Who is your Responsible Person for this task/area? | Notes | Useful resources/live links |  |  | Your notes
LEADERSHIP
Have you established a clear leadership protocol and appointed a lead member of your team to head up the management of your COVID-19 response? Against each of the points below we recommend identifying the person responsible for managing this risk. |  | The COVID-19 situation is fast evolving - effective leadership and considered, efficient and timely decisions will be critical to ensuring that your team are protected and operating efficiently and that you are working effectively with suppliers and clients to manage the risks. It will be good leadership that ensures your business remains intact after this exceptional challenge. There may be some tough decisions to make in the short-term to protect future jobs, but you are not alone and the FIS is available with access to expert advice or simply to provide a sounding board. | FIS COVID-19 Hub - this plan is designed to give you a framework to consider your COVID-19 Response, our website is updated daily with all the critical information that you will need to inform decisions | McKinsey & Co have published guidance on leadership in a crisis here | Back to work guidance
SAFETY
Do you have a clear Health and Safety Policy that covers the COVID-19 situation? |  | All businesses, regardless of size have to legally carry out a COVID-19-specific risk assessment. This will establish what safety measures you need to put in place before your people start returning to the workplace. If you have more than 50 employees, this should be published on your website. FIS has developed a Four Step Protocol to help you to establish a H&S Action Plan and policy to support safe working, to ensure that you are meeting your legal responsibilities and limiting liability for your business | FIS H&S Toolkit, includes links to latest set of site operating procedures and the FIS Four Step Protocol | FIS COVID19 Employee Welfare Policy | FIS Template Risk Assessment
Start Safe: How are you managing symptom checking on site? |  | The Information Commissioner’s Office (ICO) does allow employers to measure the temperature of an employee before allowing them to enter the worksite. This must be non-discriminatory basis and information treated as confidential medical information under the Equality Act 2010. A protocol for ensuring individuals understand risk and a process in place to formally monitor symptoms is advisable, even if it is simply a self check process that you ask workers to complete each day before arriving on site. This will also help to act as a reminder that behaviours need to change and new habits form. | FIS COVID-19 – Protocol and Checklist For Employees and Workers Arriving on Site
Start Safe: How are you deciding who should travel to work? |  | Government advice remains, where possible, people should work from home. You will need to consider what constitutes essential interaction and do all you can to protect your people and those around them. Briefing meetings that bring a number of people together at a physical location are not advisable. If people are not able work from home then it is sensible to split your teams, use multiple locations and avoid mass contamination. | Example of policy template from citation | Good Q&A available here from Croners | FIS Guidance Note for Self Employed Workers
Start Safe: How are people travelling to work? |  | One of the biggest challenges identified in FIS research is travel to work, new guidance has been made available on travelling in vehicles together and Build UK is helping TfL to manage capacity and map future requirements on public transport as more people return to work. Advice remains to avoid public transport where possible. Are you monitoring and encouraging alternative options? | Government Guidance on Safer Travel
Site Safe: Do you have a protocol in place to ensure that a site can be operated safely? |  | The CLC has produced guidelines to support this, but whether it is your site or you are working on a site managed by another contractor, it is vital that you ensure that your workers can work safely on the site. In our H&S toolkit the FIS has provided a Site Inspection Checklist and various tools to support communications with your team. Please note that additional guidance is being developed in Scotland. | CLC Site Operating Procedures | FIS Site Inspection Checklist
Site Safe: How are you communicating site teams to ensure that safety requirements are adhered to? |  | Beyond the initial restart inspection it is advisable to ensure that work continues to be carried out in a safe working environment. Guidance remains clear, if it is not safe to work then work should not continue. The FIS Site Inspection checklist can be used as a base for a daily inspection sheet for sites and offices. If problems are raised you can address speedily either directly or with the responsible contractor. If these concerns are ignored or cannot be reconciled, work should not continue. In extreme cases sites can be reported to the HSE. | FIS Site Inspection Checklist | HSE operates a whistle blowing service | A copy of the ‘Employees COVID-19 Guidance’ produced by MPA can be found here.
Task Safe: Have you reviewed all tasks and updated RAMS to cover COVID-19? |  | Having identified over a 100 work items that are currently performed in the finishes and interiors sector where it was deemed difficult to maintain the two-metre working rule, a Task Group established through specialist trade body, Finishes and Interiors Sector (FIS) reviewed methods of work and assigned a ‘traffic light’ category (red, amber, or green) to each task. | FIS H&S Task Assessment Tool
Task Safe: How are you supervising that tasks are being managed in accordance to the new RAMS? |  | It is vital to ensure that you have records that all individuals have been trained in working to the new RAMS and that supervisors are ensuring that the necessary actions and behaviours are being adhered to. Some contractors are operating yellow and red card systems for breaches of protocol. Remember COVID-19 risk is now a Riddor reportable. | FIS Methodologies for Working with COVID-19 Restrictions | CITB Toolbox Talk | A copy of the ‘Managers COVID-19 Guidance’ produced by MPA can be found
Task Safe: What PPE/RPE do your workers need and is it available? |  | With PPE / RPE in short supply and a variety of often conflicting information and advice. A key principle of new FIS Guidance is that it seeks to underpin is that, in light of difficulty sourcing PPE and RPE and the need to protect the NHS, it is vital that we identify and use the correct RPE and PPE based on task assessment and do not over specify. In this way we can protect use for tasks where higher protection is essential and ensure, wherever safe, works can continue. It is also vital that people are trained in the application, use and disposal of PPE. | FIS COVID-19 Guide to the Selection of Personal and Respiratory Protective Equipment | PPE Certificate Checklist
Other Safety Considerations: How are you ensuring that your offices/warehouse/vehicles are safe? |  | Whilst many people may continue to work from home, this is not always possible/ideal, you may wish to start to open up your office again for those where working from home may be problematic. The government, in consultation with industry, has produced guidance to help ensure workplaces are as safe as possible. These 8 guides cover a range of different types of work. Many businesses operate more than one type of workplace, such as an office, factory and fleet of vehicles. You may need to use more than one of these guides as you think through what you need to do to keep people safe. The same rigour should be applied to ensure checks and behaviours are managed as per site guidance with a regular cleaning and inspection regime in place | Working safely during coronavirus (COVID-19) | Cleaning Checklist
Have you put in place appropriate disinfecting and cleaning measures? |  | It is vital to make sure that any site or location that has been closed or partially operated is clean and ready to restart. COVID-19 can remain on surfaces long after they’ve been touched so it is important to frequently clean and disinfect facilities (including tools and vehicles as you re-open). This should include cleaning and disinfecting all frequently touched surfaces in the workplace e.g. desks, kitchen areas, bathrooms, keyboards, phones, handrails, tools and doorknobs. Workers discouraged from using other workers’ phones, desks, offices, or other tools and equipment, when possible. If necessary, clean and disinfect them before and after use. Consider providing disposable wipes so that commonly used surfaces can be wiped down by employees before each use. | FIS Site Inspection Checklist
Are you prepared for a suspected case on COVID-19 in your workplace? Has this guidance been communicated to your workforce at all sites to ensure protocol is followed and the impact limited? |  | If anyone becomes unwell with a new, continuous cough, a change in taste or smell or a high temperature in the business or workplace they should be sent home and advised to follow the stay at home guidance. If a member of staff has helped someone who was taken unwell with a new, continuous cough or a high temperature, they do not need to go home unless they develop symptoms themselves. They should wash their hands thoroughly for 20 seconds after any contact with someone who is unwell with symptoms consistent with coronavirus infection. It is not necessary to close the business or workplace or send any staff home, unless government policy changes. | Guidance on what to do if a worker displays or reports symptoms.
Are your registered first aiders briefed on how to manage the additional risks associated with COVID-19? |  | Recognising the additional risk associated with COVID-19, new guidance has been made available for first responders as defined by the Civil Contingencies Act (2004), and others who may have close contact with individuals with potential coronavirus infection (COVID-19). This includes professionals and members of voluntary organisations who, as part of their normal roles, provide immediate assistance requiring close contact until further medical assistance arrives. | COVID-19: HMG guidance for first responders | St John's Ambulance COVID-19 Advice for First Aiders | Advice from the Resuscition Council
If sites are required to close has this been done safely? |  | Companies have an obligation to minimise safety risks on sites even during shutdowns by making efforts to prevent access to the suspended site, and mitigation of any potential hazards. (remember owners of sites have a legal duty of care to any visitors, even trespassers). Note there may be additional requirements to maintain insurance for closed offices or sites. | Guidance on closing the site is available here | Guidance from the FIS on insurance matters and COVID-19
CONTRACTUAL/LEGAL MATTERS
What are you current contractual liabilities? |  | It is recommended that you conduct a review of all current and pending contracts to understand what the implications are and what any liabilities may be for your business as a result of any delays to the programme. | Guidance on Contractual Issues Caused by Coronavirus (England) | Guidance on Contractual Issues Caused by Coronavirus (Scotland) | FIS Legal Helpline - 0121 707 0077
Are you aware of and strictly adhering to notification periods for delays and any potential cost over-runs? Are you adding sensible warnings to any project updates? |  | Whilst the potential for delay may seem obvious, it is vital that you continue to follow your contractual responsibilities and many contracts will provide express guidance on early warning of delays. Any request for an extension should make note of the provisions within the contract | FIS Contractual and Legal Toolkit | FIS Webinars
Have you considered putting in place the vital documentation to support notification of delay or suspension? |  | Any agreements outside the terms of the contract must be properly recorded. Note that the people you are dealing with now, may not be those dealing with this later , if trade liquidators, funders etc get involved 1. Make sure any payment and payless notice are issued on time 2. Warn your colleagues against making rash statements under any circumstances such as “ I m not paying you and that's that” ( downstream) or "I am leaving” (Upstream) or "just leave" or anything like it as this could be construed as a repudiatory breach of contract 3. JCT standard 2016 unamended extension of time clauses allow EOT for • change of Law that directly affects the execution of the works • and for Force Majeure ( Act of God) 4. No loss and expense entitlement associated with these Relevant Events but obviously no LAD’s can be levied 5. Either Party may terminate their Employment ( not terminate the Contract) if the works are suspended by 2 months or other period stated in the particulars again for Force Majeure or change of law as above. The relevant Notices must be issued which come into effect 7 days after the date of the Notice 6. Following termination no further payments are due to the Contractor and a final account must be provided within the timescale set out. The account can include for any direct loss and expense caused to the Contractor by the termination | FIS Contract Health Check Tool | Detailed Claim Template
Are potential liabilities covered by Force Majeure? Are you aware of the process for invoking force majeure? |  | Where there are force majeure provisions within most standard forms of contract, the events are usually defined. This is often a long list including acts of God, flood, drought, earthquake and so on. Sometimes, it includes failure or interruption of utility services or non-performance of suppliers or sub-contractors. In light of Covid-19, businesses need to reassure themselves that the force majeure definition includes epidemic or pandemic or civil emergency or similar. In the absence of such knowledge, then it may be the case that a business can rely on action taken by the government or a public authority (for example a government announcement on travel restrictions which may prevent a business from fulfilling its contractual obligations). | Excellent article published in Construction Enquirer on Force Majeure and contract provision here
SUPPLY CHAIN
Do you have a list of products that are essential to the smooth operation of your business? Are any in short supply and could this delay your work? |  | Consider producing an inventory of all products that you buy and use that are essential to your business (core components, fixings, tools, PPE etc) - have any alerts been issued by your supply chain. It is important to consider the liability and to ensure that any delays are notified in accordance with the contract
Are you monitoring productivity related to new ways of working, how will this impact your ability to deliver on existing contracts and how are you factoring this into future estimates? |  | Adhering to guidance in the Site Operating Procedures may slow down working or require additional tools or equipment. How is this likely to impact your productivity, can you afford to operate at pre COVID-19 rates? | FIS Legal Helpline - 0121 707 0077
How are you allowing for pandemic risk in future contracts? |  | It is sensible for companies to be proactive and try to ensure that there is protection in their contracts against the effects of Covid-19. ClarksLegal has provided an example clause, for inclusion in tender packages. | Covid-19 clause – extensions of time and additional cost
CASHFLOW
How are you forecasting potential cash implications? Are you up to date on your credit control? |  | It is recommended to get a clear picture of your overheads and start projecting cash flow based on possible scenarios. If you are not having joy with client Accounts departments, take things back to your main contacts and chase at every point. | The Small Business Commissioner operate the Prompt Payment Charter and can put pressure on larger companies to meet their requirements | McKinsey & Co have started to look at likely scenarios here | The next sheet on this tool looks at some key cash flow considerations
Are you aware of the scope of support available from UK Government? |  | An extensive package of support is available to businesses to help them to trade through this period. More details are available on the FIS COVID-19 Hub. Some elements of support, such as Business Rate Relief are at the discretion of the local authority and have been accessed for some members due to the impact of closures in hospitality and retail on their work | See Government Support Packages in the FIS COVID-19 hub
Have you looked into the possibility of an interest free loan? |  | To date around 55% of FIS Members who have applied have successfully received one of the Government Loan products. Whilst you may not need this money now, the cost of restart may require you to dip into your reserves. Most of the Government products are interest free for 12 months? | See Government Support Packages in the FIS COVID-19 hub
Have you spoken to suppliers about how they are intending to manage credit during this period? |  | FIS is contacting suppliers to understand the support that they can offer to the supply chain, but if you have concerns it is advisable to pick up the phone to understand what assistance they may be able to give. The recent announcement that reinsurance options are open to support credit guarantee will help to support cash flow through the sector | Recent FIS Webinar on Surviving the Crisis
Have you looked into the possibility of claiming R&D Tax Credits? |  | Many companies are surprised to learn that they qualify for this valuable source of funding, so it could pay to double-check. In fact, ForrestBrown has helped FIS members receive over £3.5m in R&D tax credits. | More information on how to start an R&D Tax Credit Claim is available here | View our recent webinar on R&D Tax credits
What do your current employment contracts offer in terms of Statutory Sick Pay and extended periods where individuals cannot work? |  | It was announced in the Budget that Government would meet the cost of coronavirus statutory sick pay (SSP) for small businesses with up to 250 employees for 14 days. Processes to support this are currently being developed in the meantime you are encouraged to maintain comprehensive records | Advice on SSP and Universal Credit here | FIS Legal Helpline - 0121 707 0077
Have you spoken to your insurance broker about any cover that you may have in place? |  | In terms of cover for Business Interruption, for cover to exist members would need to have purchased an extension called “Notifiable Diseases Extension” as the government has declared COVID 19 a notifiable disease. This extension is usually only offered/bought in the leisure sector by Hotels, Restaurants, Sporting Venues etc, where profit is driven by foot fall. It is rare for this extension to have been purchased in the construction/manufacturing/wholesale sector.
If you are closing your office, have you advised your insurer? |  | For those businesses who have had to close for the foreseeable future – please check your insurance cover. Some policies have specific clauses around vacancies and how many days you are allowed. This is particularly important If you have stock on site. Some businesses have had to make some amendments to their policies to ensure they have sufficient cover.
In a worst case scenario what is the provision within your employment contracts to furlough (through the Coronavirus Job Retention Scheme), lay-off staff or request shortened working hours and how quickly can you implement change? |  | There are a number of options before you consider redundancy and it is likely your employment contracts will set the parameters for evoking these. It is critical that you adhere closely to the rules set out in your contract and if you wish to retain people for when things scale back, up that you communicate clearly and they understand the reasons for your decisions. Furlough provides an option that is essentially an enhanced lay-off option and is relatively straightforward as long as the employment contract allows this - a furloughed employee cannot do any work for the business. Short-time working is when an employee works reduced hours or is paid less than half a week’s pay. Laying off staff or short-time working can help avoid redundancies - but you have to agree this with staff first. | Details of the Coronavirus Job Retention Scheme | See the section on employment on the FIS COVID-19 Hub | FIS guidance on short-time working, lay-off and redundancy including template resources
Have you considered a process for re-opening the business? |  | Work will pick up and it is important that we start preparing now to meet and manage the various priorities that will emerge in the future.
PEOPLE
Do you have a clear and relevant internal communication plan in place? |  | With office teams more disparate and communication with site teams on safety and programme issues never more important, do you have a communication plan? This should focus on two-way communication, namely ensuring your workforce are briefed on all COVID issues and policies, but also enable individuals and teams are able to feed in concerns that they may have. Critical is that everybody understands their responsibilities and feels they have a voice in operation restart and they are not scared to air concerns, this could be vital information. It is worth considering setting up a cross company task group, just to ensure all parts of the team feel they have a voice and concerns are immediately assessed and addressed before they become problems. It may be sensible to have a nominated internal contact to consolidate and collate questions raised about COVID-19. This may be separate from leader to help ensure that issues can be looked at the in wider context and there is not pressure to make on the spot decisions when reflection is needed. | Communicating in a crisis | Coronavirus: over 20 key HR questions answered
For those now working from home have you sent guidance and do they have clear tasks that can be completed and measured? |  | Many people may not be working from home and could find it difficult to motivate and slip into bad habits particularly over time, maintaining a team dynamic is also more difficult. How is this being monitored? Are you having regular calls? Are you monitoring login times? Do you have regular team calls and check in one-to-one? Do you have a mechanism for monitoring the mental health of your team? | FIS Working From Home Guidance | ACAS advice on homeworking
If you are asking certain staff members to work from home, do you have sufficient work to maintain them full time? How will you monitor their productivity? |  | Working from home in the short term to complete tasks is relatively easy to manage, but longer term it may become more challenging to ensure that there is sufficient work and that you are able to monitor their performance. FIS recommends use of the RACI model to manage tasks and responsibilities. | FIS Template RACI model
Have you started to open a dialogue about the criteria that you will apply to a return to the office? |  | There are a number of considerations when asking people to return, will they be safe, but also will they feel safe. Particularly those that have not been required to leave the house may feel apprehensive. Do you know currently how far and how they travel to work? With uncertainty over the return of schools and sensitivities around returning children to school, policies on flexible working may need to be revisited. Are there any benefits to home working that you may wish to capitalise on, the likelihood is also that more people will feel they can work from home more effectively in the future, is this the case, does your current policy need reviewing? | Advice on managing return to work of long term absent workers, joint advice from the HSE and CIPD | ACAS Guide to Responding to a Flexible Working Request
How are you communicating with Furloughed workers? |  | This is an unusual situation all round and all aspects need to be managed. Different people will be reacting in different ways, but it is important whilst someone remains on Furlough that they feel part of your team (whilst retaining a strict no fee earning work rule). Mental health issues and alcohol reliance are all considerations. Some may be raring to go, others apprehensive about the return. | Guide to communicating with furloughed workers
Will you need to make Furloughed worker redundant? |  | Employers can make employees redundant while they are ‘on furlough’ or immediately after. If an employee is made redundant while on furlough, their redundancy rights are not affected. If you need to make a furloughed worker redundant, you will need to follow an appropriate consultation process and adhere to strict legal protocol. | FIS Employment Toolkit includes advice on Redundancy
How are you liaising with Furloughed workers around returning to work? |  | The scheme has been extended until the end of July on the current basis and on a different basis until the end of October. Full details of changes are not available at this stage, but we understand it will include some option to return on reduced hours. Some workers will be keen to return, others may be apprehensive, it is sensible to speak to individuals and agree a return date. There is no notice period written into law a notice period of at least 48 hours should be considered to ensure any concerns are discussed and if possible addressed. | Guide to communicating with furloughed workers
In the case of a need to self-isolate (or care for a family member) have you checked, wherever possible, key team members are prepared for remote working (i.e. access to systems, suitable broadband and telephone connections)? |  | Are phone systems operable and can you connect people in a remote environment. Is there sufficient access to key information? Are connections secure? Are there key roles in the business that cannot be managed remotely? | Stay at home guidance from Government has been provided here | Advice on Statutory Sick Pay
Have you reviewed all of your GDPR policies to account for the fact that individuals will be working away from the office? Are you cyber secure? |  | Measures announced over recent weeks to deal with coronavirus (COVID-19) have seen our day-to-day life drastically changed – we are spending more time at home and online. Unfortunately, criminals will use every opportunity they can to scam innocent people and their businesses. New guidance from HMG explains simple steps you can take to protect yourself and your business against fraud and cyber crime and where to get help. | HMG Advice on Cyber Crime | New Guidance from the National Centre for Cyber Security
If someone is sick or is required to self-isolate, what are the rules around payment and Statutory Sick Pay (SSP)? |  | Ultimately your employment contracts and handbooks should determine your company policy, but companies can now again claim back SSP for two weeks. This will not cover the full salary if you have opted to be more generous in your contracts | Certifying absence from work and SSP, the official guidance | FIS Employment Law Toolkit (including FAQ)
Are there any members of your team that fall into the more vulnerable groups that need additional consideration? |  | Employees from defined vulnerable groups should be strongly advised and supported to stay at home and work from there if possible. You may also want to consider policies for those who live with people who are older or have underlying health issues. | Who currently falls into the list of vulnerable groups | Guidance on shielding and protecting people who are clinically extremely vulnerable from COVID-19
Are your records/project files up-to-date and accessible to all team members? Do you have up-to-date contact details for people who may need to isolate at short notice? |  | When there is imminent risk that key individuals may be unavailable at short-notice, record keeping is more important than ever as it enables colleagues to step in with minimal upheaval
Do you have a mental health policy? |  | If you have mental health first aiders, it is worth re-enforcing who they are and parameters for contacting them. | Visit the FIS Mental Health Hub | Mates in Mind COVID-19 Mental Health Toolkit
If we've missed anuthing or you come across some additional advice that would help improve this list or you need clarification, please email iainmcilwee@thefis.org

## Cash Flow Considerations
Income
Credit control – is everything up to date, RAG what you think will and might not come in
Are you in a strong position to defend in the case of pay-less notices
Outgoings
Look at all possible lines of support from Government - we still do not know how long this will go on, so consider going early rather than waiting for a crisis. Pay attention to the terms of loans, but note they should be 12 months interest free loans
Speak to your key suppliers and identify what payment terms may be available to support you
Rent & Mortgages: Have you spoken to your landlord/mortgage provider to look at deferrals and holidays
Business Rates, might still be worth talking to the local authority if you can demonstrate your business is heavily reliant on the sectors in scope, you may be able to argue you are part of that sector (note showrooms are included too) – basically there may be some wiggle room
Tax deferral is possible - look at the options under Time to Pay
Employment Matters - Furlough anyone that you need to – remember you can top up the rest if you want to, so doesn’t have to disadvantage people (depending on how you pay yourself this may be an option for you, but remember if you are caught working it could be considered fraud). Short-time also an option if there is a basic skeleton staff need
It has been suggested that talking to staff about pension contributions is possible, note you have legal obligations, both in terms of contracts and statutory obligations
Contact utilities to see how they intend to support you through (could you scale back mobile contracts etc, especially if you are furloughing staff?)
If your turnover is likely to drop, will your insurer reduce your premium accordingly?
Lease agreements may be relaxed, several vehicles suppliers are already relaxing terms, offering holidays and extending time periods
CITB levy is on a three month holiday